## Gantt Chart
SecureStock: Dual-Biometric Sequential Access and Materials Accountability System
Project Gantt Chart for July 20, 2026 to October 14, 2026. 13 weeks, 38 work sessions, 186 total hours. Sessions: Monday 7:30-10:30 AM (3 hours), Wednesday 7:30-10:30 AM (3 hours), Sunday 8:00 AM-5:00 PM (9 hours).
ID | Task | Phase | Start | End | Hours | W1 |  |  | W2 |  |  | W3 |  |  | W4 |  |  | W5 |  |  | W6 |  |  | W7 |  |  | W8 |  |  | W9 |  |  | W10 |  |  | W11 |  |  | W12 |  |  | W13
[6 empty] | M 20 | W 22 | Su 26 | M 27 | W 29 | Su 2 | M 3 | W 5 | Su 9 | M 10 | W 12 | Su 16 | M 17 | W 19 | Su 23 | M 24 | W 26 | Su 30 | M 31 | W 2 | Su 6 | M 7 | W 9 | Su 13 | M 14 | W 16 | Su 20 | M 21 | W 23 | Su 27 | M 28 | W 30 | Su 4 | M 5 | W 7 | Su 11 | M 12 | W 14
P1 Planning and Feasibility
1 | Project kickoff, team roles and RACI | P1 | 2026-07-20 | 2026-07-22 | 6
2 | Problem definition and feasibility study | P1 | 2026-07-20 | 2026-07-26 | 15
3 | Project charter and scope sign-off | P1 | 2026-07-22 | 2026-07-26 | 12
P2 Requirements Analysis
4 | Faculty interview | P2 | 2026-07-26 | 2026-08-02 | 24
5 | Functional and non-functional requirements | P2 | 2026-07-27 | 2026-08-02 | 15
6 | SRS document and approval | P2 | 2026-08-02 | 2026-08-09 | 24
P3 System Design
7 | System architecture and data flow diagrams | P3 | 2026-08-03 | 2026-08-09 | 15
8 | Database design (ERD) and schema review | P3 | 2026-08-03 | 2026-08-09 | 15
9 | Hardware schematic and wiring diagram | P3 | 2026-08-05 | 2026-08-16 | 27
10 | UI and UX wireframes, design review | P3 | 2026-08-09 | 2026-08-16 | 24
11 | SDD document and sign-off | P3 | 2026-08-10 | 2026-08-16 | 15
P4 Implementation
12 | Source suppliers and finalize BOM | P4 | 2026-07-27 | 2026-08-02 | 15
13 | Order hardware components | P4 | 2026-08-03 | 2026-08-05 | 6
14 | Receive and inspect components (lead time) | P4 | 2026-08-10 | 2026-08-23 | 30
15 | Backend refinement and security hardening | P4 | 2026-08-17 | 2026-09-06 | 45
16 | Frontend refinement and dashboard polish | P4 | 2026-08-17 | 2026-09-06 | 45
17 | Firmware: fingerprint sensor driver | P4 | 2026-08-24 | 2026-09-06 | 30
18 | Firmware: I2C LCD, buttons, Wi-Fi, NTP | P4 | 2026-08-24 | 2026-09-06 | 30
19 | Firmware: device API client and enrollment | P4 | 2026-08-31 | 2026-09-13 | 30
20 | Circuit assembly: door node and relay lock | P4 | 2026-09-07 | 2026-09-20 | 30
21 | Circuit assembly: box node, solenoid driver | P4 | 2026-09-07 | 2026-09-20 | 30
22 | Enclosure fabrication and mounting | P4 | 2026-09-14 | 2026-09-27 | 30
23 | Hardware and software integration | P4 | 2026-09-14 | 2026-09-27 | 30
P5 Testing (V and V)
24 | Unit and integration testing | P5 | 2026-09-07 | 2026-09-20 | 30
25 | System testing: door to box sequential gate | P5 | 2026-09-21 | 2026-10-04 | 30
26 | Security testing: tailgating, expired session | P5 | 2026-09-21 | 2026-10-04 | 30
27 | Defect fixing and regression retest | P5 | 2026-09-28 | 2026-10-04 | 15
P6 Documentation and Defense
28 | User manual and technical documentation | P6 | 2026-09-28 | 2026-10-07 | 21
29 | Defense preparation, dry run and rehearsal | P6 | 2026-10-08 | 2026-10-12 | 12
30 | FINAL DEFENSE and system demonstration | P6 | 2026-10-14 | 2026-10-14 | 3
LEGEND (SDLC phases) | [8 empty] | Group Members:
P1 | Planning and Feasibility | [7 empty] | Aballa, Gerjhon
P2 | Requirements Analysis | [7 empty] | Abragan, John Lloyd
P3 | System Design | [7 empty] | Cuenca, John Adam A.
P4 | Implementation | [7 empty] | Subject: CPE 048: Embedded Systems
P5 | Testing (V and V) | [7 empty] | Section: COC-FA-CPE4-01
P6 | Documentation and Defense